## 📋 How to Use
📋 HOW TO USE: SOP — Concrete Pour
ABOUT THIS TEMPLATE
Standard Operating Procedure checklist for concrete pours. Print this for every job and have your foreman check off each step. Covers pre-pour prep, morning of pour, during pour, finishing, and cleanup.
STEP-BY-STEP INSTRUCTIONS
1. | Print a copy for each job
2. | Fill in the Job name, Date, Foreman, and Crew Size at the top
3. | Work through each phase chronologically
4. | Check off (✓) each completed task in the yellow column
5. | Note the time each task is completed
6. | Add any job-specific notes in the Notes column
7. | Keep completed checklists in your job files for reference
🟡 YELLOW CELLS = Editable (enter your data here)
📊 CELLS WITH FORMULAS (don't overwrite): None — this is a checklist template
✏️ EDITABLE CELLS: Done (✓), Time, and Notes columns (yellow)
TIPS FOR PRINTING / PDF EXPORT
• File > Print or Ctrl+P to print
• Set to 'Fit Sheet on One Page' for best results
• Use 'Portrait' orientation for estimates and contracts
• Use 'Landscape' for pricing matrices and marketing plans
• To save as PDF: File > Save As > PDF format
• Print Preview first to check margins and page breaks
🔗 MORE FREE TOOLS: https://estimateconcrete.com
Free concrete calculators, estimating guides, and contractor resources

## SOP - Concrete Pour
STANDARD OPERATING PROCEDURE — CONCRETE POUR
Job: |  | Date:
Foreman: |  | Crew Size:
PRE-POUR (Day Before) |  | Done (✓) | Time | Notes
1 | Confirm concrete delivery time with batch plant
2 | Verify total cubic yards ordered (include 10% waste)
3 | Check weather forecast — no rain within 24 hours
4 | Verify all forms are set, level, and properly staked
5 | Confirm rebar/mesh is installed and inspected
6 | Verify gravel base is compacted and graded
7 | Check that control/expansion joints are planned
8 | Load all tools and equipment on truck
9 | Confirm crew availability and arrival time
10 | Contact client to confirm pour date
MORNING OF POUR (Before Concrete Arrives) |  | Done (✓) | Time | Notes
1 | Arrive at job site minimum 1 hour before truck
2 | Walk the site — check forms haven't shifted overnight
3 | Wet down gravel base (prevents concrete from drying too fast)
4 | Set up all finishing tools within reach
5 | Assign crew positions (rake, vibrate, screed, finish)
6 | Verify pump truck is set up (if using pump)
7 | Check access route for concrete truck
8 | Have water source ready for tools and cleanup
9 | Apply release agent to forms
DURING POUR |  | Done (✓) | Time | Notes
1 | Guide concrete truck into position
2 | Direct concrete placement — start at far end, work back
3 | Vibrate concrete to remove air pockets
4 | Screed to proper grade as pour progresses
5 | Monitor concrete consistency — reject if too dry or wet
6 | Keep track of yards placed vs. ordered
7 | Bull float immediately after screeding each section
8 | Install control joint inserts or mark for cutting
9 | Keep pour moving — don't let concrete set before finishing
10 | Get concrete truck driver's ticket (record yards delivered)
FINISHING |  | Done (✓) | Time | Notes
1 | Wait for bleed water to evaporate before finishing
2 | Test readiness — kneeboard should leave 1/4" impression
3 | First pass with fresno or mag float
4 | Edge all perimeter and joint locations
5 | Apply broom finish or stamp pattern
6 | Cut or tool control joints (1/4 of slab depth)
7 | Apply curing compound or wet cure
8 | Protect fresh concrete from rain/frost if needed
9 | Remove forms after 24 hours minimum
CLEANUP & CLOSE-OUT |  | Done (✓) | Time | Notes
1 | Wash all tools immediately — don't let concrete harden
2 | Clean concrete truck chute area
3 | Remove all debris and excess material
4 | Take completion photos (multiple angles)
5 | Note any issues or deviations on this checklist
6 | Apply sealer after 28-day cure (if contracted)
7 | Schedule client walkthrough
8 | Submit final invoice
ADDITIONAL NOTES: